AI Clinical Memory Platform

Solo Founder MVP Build Plan

A step-by-step operating document for building the MVP with ChatGPT, Codex, and AI tools

| Prepared for | Neelesh - solo founder |
| --- | --- |
| Product idea | AI Clinical Memory Platform for Indian doctors |
| MVP wedge | Diabetes/endocrinology or another follow-up-heavy specialist clinic |
| Core promise | Press start, consult naturally, review a reliable note, and begin the next follow-up with full patient context. |
| Version | 1.0 - 2026-07-12 |

FOUNDER RULE: The AI output is always a draft. The doctor-approved output is the final clinical record.

Use this document as your build checklist, roadmap, prompt library, and pilot operating plan.

# 1. The MVP You Should Build First

Do not build the full long-term platform immediately. Your first job is to prove that a doctor will repeatedly use, trust, and pay for a narrow workflow: record a consultation, get a structured note, approve it, and see useful context before the next follow-up.

MVP DEFINITION: A doctor can record a consultation, receive a structured clinical draft note, edit and approve it, and later see a patient memory summary before the follow-up.

## The first workflow

Doctor logs in.

Doctor opens or creates a patient profile.

Doctor clicks Start Recording.

Consultation happens naturally without interruption.

Doctor clicks Stop Recording.

The system transcribes the audio.

AI converts the transcript into a structured draft clinical note.

Doctor edits and approves the note.

The approved note updates the patient timeline.

Before the next visit, the doctor sees a concise follow-up memory summary.

## MVP success statement

Doctor opens patient profile -> clicks Start Recording -> consultation happens -> AI prepares note -> doctor edits and approves -> next visit shows previous context.

## Must-have, should-have, and later

| Priority | Build | Why it matters |
| --- | --- | --- |
| Must-have | Doctor login; patient creation; consultation recording; audio upload; transcription; structured draft note; edit and approve; patient timeline; follow-up memory; printable/downloadable note. | This proves the core value: documentation savings plus continuity of care. |
| Should-have | WhatsApp sharing; email sharing; doctor-specific templates; medication extraction confidence; pending investigations; clinic assistant role. | These improve workflow adoption after doctors already like the core product. |
| Do not build now | Patient app; diagnosis suggestions; prescription recommendations; billing; pharmacy ordering; lab integrations; hospital ERP integrations; ABDM integration. | These increase complexity before the main behavior is validated. |

## Positioning

Start with a narrow positioning statement:

AI Clinical Memory for Indian diabetes doctors. Alternative: AI follow-up memory and documentation assistant for busy specialist clinics.

# 2. Solo-Founder Operating Model

As a solo founder, your advantage is speed. Your risk is scope creep. Treat AI tools as a compact founding team, but keep human judgment for medical safety, customer discovery, and product decisions.

| Role | Responsibility | How to use it |
| --- | --- | --- |
| You | Founder, product owner, doctor researcher, final reviewer. | Make all product trade-offs. Talk to doctors. Review every Codex change before merging. Decide what is in and out of scope. |
| ChatGPT | Product manager, prompt engineer, QA reviewer, research analyst, sales writer. | Use it to write PRDs, doctor interview scripts, clinical templates, prompts, QA checklists, pilot plans, and demo scripts. |
| Codex | Junior engineering team. | Give it small GitHub tasks: build pages, APIs, schema, tests, fixes, and refactors. Do not ask it to build the whole startup at once. |
| Doctors | Domain validators. | Use doctors to validate pain, note format, workflow, willingness to pay, and clinical trust. |
| Lawyer/security reviewer | Part-time compliance and privacy reviewer before real patient data scale. | Review consent, privacy policy, retention, breach process, and agreements before live clinic use. |

## Golden operating rule

SCOPE DISCIPLINE: One specialty, one doctor type, one consultation workflow, one killer feature: follow-up memory.

## Recommended weekly rhythm

| Day | Founder focus | AI tool usage |
| --- | --- | --- |
| Monday | Choose the week's feature scope and acceptance criteria. | Ask ChatGPT to convert ideas into PRDs and tickets. |
| Tuesday to Thursday | Build and test the selected features. | Use Codex for coding tasks and ChatGPT for debugging plans and prompt iteration. |
| Friday | Test with synthetic consultation data and edge cases. | Ask ChatGPT to compare transcripts against generated notes and find hallucinations. |
| Saturday | Show progress to doctors or collect feedback. | Ask ChatGPT to summarize feedback into insights, objections, and product changes. |
| Sunday | Update roadmap, backlog, and next sprint. | Ask ChatGPT to reprioritize based on adoption evidence. |

# 3. MVP Phases

Build in phases. Each phase has a clear learning goal and a shipping gate. Do not move forward just because the code works; move forward when the customer signal supports it.

| Phase | Goal | Deliverables | Exit criteria |
| --- | --- | --- | --- |
| Phase 0: Founder setup | Create the operating system for building. | ChatGPT Project, GitHub repo, backlog, sample transcripts, README, PRODUCT, ROADMAP, AGENTS file. | You can give Codex precise tasks and keep all context in one place. |
| Phase 1: Doctor validation | Confirm pain, workflow, recording comfort, and willingness to try. | 15 to 20 doctor interviews; notes; objections; top specialty pain points. | At least 3 to 5 doctors say, "I want to try this in my clinic." |
| Phase 2: Clickable prototype | Validate screens before backend complexity. | Mock screens: patient profile, record, processing, note editor, timeline, follow-up memory. | Doctors understand the workflow without explanation and ask for a trial. |
| Phase 3: Technical MVP | Make the audio-to-note loop work. | Auth, patients, recording, upload, transcription, AI note JSON, note editor, approval state. | Synthetic consultations produce useful notes with minimal hallucination. |
| Phase 4: Patient memory | Turn notes into longitudinal memory. | Timeline events, previous visit summary, medication changes, pending tests, follow-up view. | Doctor can prepare for a follow-up in under 30 seconds. |
| Phase 5: Pilot | Measure real workflow value. | 2 to 3 clinic pilot, consent process, support channel, usage metrics, feedback form. | Doctor uses it repeatedly and says they would pay. |
| Phase 6: Paid conversion | Convert usage into revenue. | Pricing, monthly plan, onboarding, support process, basic legal docs. | At least one pilot customer pays or commits to pay. |

## Do not skip Phase 1

The biggest failure mode is building a technically impressive tool that doctors do not adopt. Doctor interviews and prototype reviews are not optional; they are how you discover what must be automated, what must stay editable, and what doctors will pay for.

# 4. First 30-Day Execution Plan

| Days | Objective | Tasks | Output |
| --- | --- | --- | --- |
| 1 to 3 | Narrow the MVP. | Choose first specialty; define single user persona; write positioning; remove non-MVP features. | One-page MVP scope document. |
| 4 to 7 | Talk to doctors. | Interview 10 doctors; ask about documentation, follow-up memory, recording concerns, and willingness to pay. | Customer discovery notes and top 5 pain points. |
| 8 to 10 | Build mock prototype. | Create screens with mock data: patient profile, recording, draft note, timeline, follow-up memory. | Clickable demo for doctors. |
| 11 to 18 | Build core pipeline. | Implement auth, patient profile, audio recorder, upload, transcription, structured extraction, note editor. | Technical MVP working on synthetic data. |
| 19 to 23 | Add safety and privacy basics. | Consent checkbox, private storage, audit logs, doctor approval states, deletion option, AI draft disclaimer. | Pilot-safe workflow foundation. |
| 24 to 30 | Prepare pilot. | Create onboarding guide, consent text, demo video, support channel, feedback form, pilot scorecard. | Ready to onboard 2 to 3 friendly clinics. |

## 30-day completion checklist

[ ] Specialty selected.

[ ] 10 doctor interviews completed.

[ ] Clickable prototype shown to at least 5 doctors.

[ ] GitHub repo created and connected to Codex.

[ ] ChatGPT Project created with all founder notes and requirements.

[ ] Synthetic consultation transcript set created.

[ ] Audio recording and upload working.

[ ] Transcription working on test audio.

[ ] AI note JSON generated from transcript.

[ ] Doctor edit and approval workflow working.

[ ] Patient timeline created from approved notes.

[ ] Follow-up memory summary working.

[ ] Consent text and AI draft disclaimer added.

[ ] Pilot scorecard prepared.

# 5. How to Use ChatGPT

Use ChatGPT as your product, strategy, QA, and writing partner. Keep a dedicated ChatGPT Project for this startup so your founder notes, PRDs, doctor feedback, sample transcripts, and prompt library stay together.

## What to keep inside the ChatGPT Project

Founder notes and long-term vision.

This MVP build plan.

Doctor interview notes.

Sample and synthetic consultation transcripts.

Specialty templates.

Database schema.

Prompt versions and test outputs.

Pilot feedback and weekly decisions.

## Core ChatGPT workflows

| Workflow | Use ChatGPT for | Example prompt |
| --- | --- | --- |
| Product specs | Turn product ideas into buildable PRDs. | Act as my product manager. Write a PRD for [feature] with user stories, screens, database changes, APIs, edge cases, privacy risks, acceptance criteria, and tests. |
| Clinical templates | Create specialty-specific note structures. | Create a diabetes follow-up note template for an Indian private clinic. Include complaint, history, vitals, investigations, medications, lifestyle advice, follow-up, and patient instructions. |
| Prompt engineering | Improve note-generation prompts and reduce hallucination. | Improve this prompt so the AI extracts only what was explicitly said and adds unclear information to uncertain_items. |
| QA review | Compare transcript and generated note. | Compare this transcript and AI note. Identify hallucinations, missing medications, wrong instructions, unsafe assumptions, and unclear items. |
| Doctor feedback | Convert interviews into insights. | Turn these doctor interview notes into pain points, objections, buying signals, feature requests, and next experiments. |
| Sales/demo | Create scripts and onboarding material. | Create a 10-minute demo script for an endocrinologist showing how this saves time during follow-ups. |

## Prompt: Feature PRD generator

Act as my product manager. Write a detailed PRD for this feature: [FEATURE] Include: - user story - why it matters - screens - database changes - API endpoints - edge cases - privacy risks - acceptance criteria - test cases Context: This is an AI clinical memory MVP for Indian specialist doctors. AI must not diagnose or prescribe. Doctor approval is mandatory.

## Prompt: Transcript-to-note QA

Compare the transcript and AI-generated note below. Find: 1. Hallucinated facts. 2. Missing complaints. 3. Missing or incorrect medications. 4. Wrong dosage or frequency. 5. Missing investigations. 6. Unsafe assumptions. 7. Items that should be moved to uncertain_items. Return a table with: issue, severity, transcript evidence, suggested fix. Transcript: [PASTE TRANSCRIPT] AI note: [PASTE NOTE]

# 6. How to Use Codex

Use Codex as your coding agent. It can read, edit, run, and review code, and in cloud/GitHub workflows it can work against a repository and create pull requests. Give it small, specific tasks with acceptance criteria.

IMPORTANT: Do not ask Codex to build the whole startup. Ask it to complete one small ticket at a time.

## Good Codex task examples

Create the database schema for clinics, doctors, patients, consultations, transcripts, AI notes, approved notes, timeline events, and audit logs.

Build a Next.js patient profile page with demographics, consultation timeline, and start consultation button.

Add an audio recorder component that records from the browser microphone and uploads the audio file.

Create an API route that sends audio to the transcription service and stores the transcript.

Build a note editor where the doctor can edit the AI-generated note before approving.

Add row-level security so doctors can only see patients from their clinic.

Write tests for the consultation creation API.

## Bad Codex task examples

Build the full clinical memory platform.

Add all hospital integrations.

Make the AI diagnose and prescribe.

Refactor everything and improve the UX.

Fix all bugs without changing behavior.

## Repository AGENTS.md

Create an AGENTS.md file in the repo root so Codex understands the product constraints and coding rules.

# AI Clinical Memory MVP - Coding Rules ## Product This is a clinical documentation assistant for doctors. It must not diagnose, prescribe, or recommend treatment. ## Stack - Next.js - TypeScript - Tailwind CSS - Supabase Postgres - Supabase Auth - OpenAI API - Vercel deployment ## Rules - All patient data must be scoped to clinic_id. - Never expose raw audio publicly. - Use signed URLs for audio files. - Every AI-generated note must have status: draft, edited, approved, or rejected. - Doctor approval is required before final note generation. - Add audit logs for create, edit, approve, delete actions. - Write safe fallback error messages. - No medical recommendations in code or prompts. ## Testing Run: npm run lint npm run test npm run build

## Codex ticket template

Title: [Small feature or bug] Context: This is an AI clinical memory MVP for Indian specialist doctors. AI output is draft only. Doctor approval is required. Task: [Describe exactly what to build or fix.] Requirements: - [Requirement 1] - [Requirement 2] - [Requirement 3] Files likely to change: - [file/path] Acceptance criteria: - [Expected behavior] - [Privacy/security expectation] - [Error state] Testing: Run npm run lint, npm run test, and npm run build. Do not change unrelated files.

# 7. Recommended MVP Tech Stack

Choose boring, fast, well-documented tools. Your goal is to validate workflow and trust, not to prove a complex architecture.

| Layer | Recommended choice | Reason |
| --- | --- | --- |
| Frontend | Next.js, TypeScript, Tailwind CSS, shadcn/ui | Fast to build, common patterns, easy for Codex to work with, good for dashboards and forms. |
| Backend | Next.js API routes first | Keeps the MVP simple. Move heavy processing to background jobs later. |
| Database | Supabase Postgres | Managed Postgres, auth, storage, and row-level security are useful for a solo founder. |
| Auth | Supabase Auth | Supports doctor/clinic login and role-based access. |
| Storage | Supabase Storage or S3-compatible private storage | Store audio privately with signed URLs. Avoid public files. |
| AI | OpenAI API for transcription/structuring plus deterministic validation logic | Use API workflows for the production product. Use ChatGPT for internal planning and prompt testing. |
| Deployment | Vercel plus Supabase | Fast deployment and easy iteration. |
| Monitoring | Sentry and privacy-safe product analytics | Track errors and usage without recording sensitive clinical content. |

## Simple architecture

Doctor browser -> records consultation audio Next.js app -> uploads audio Private storage -> sends audio for transcription Transcription service -> returns transcript AI structuring pipeline -> extracts complaint, history, meds, tests, advice, follow-up Draft clinical note -> doctor edits and approves Approved note + patient timeline -> shown before next follow-up Follow-up memory summary

## The key product boundary

BOUNDARY: AI-generated content is draft documentation. It is not diagnosis, prescription, triage, or independent medical advice.

# 8. MVP Data Model

Start with a simple schema that supports clinic-level access control, draft-to-approved note states, timeline events, and auditability.

| Table | Purpose | Key fields |
| --- | --- | --- |
| clinics | Represents a clinic or single-doctor practice. | id, name, address, phone, created_at |
| doctors | Doctor users linked to clinics. | id, clinic_id, name, specialty, email, phone, created_at |
| patients | Patients within a clinic. | id, clinic_id, name, age, gender, phone, external_patient_id, created_at |
| consultations | One visit or interaction. | id, clinic_id, doctor_id, patient_id, visit_date, visit_type, status, created_at |
| audio_files | Private audio references. | id, consultation_id, storage_path, duration_seconds, language_hint, created_at |
| transcripts | Raw and cleaned text. | id, consultation_id, raw_text, cleaned_text, confidence_notes, created_at |
| clinical_notes | AI draft, doctor-edited note, approved note. | id, consultation_id, ai_draft_json, doctor_edited_json, approved_text, status, approved_by, approved_at, created_at, updated_at |
| patient_timeline_events | Longitudinal memory objects. | id, patient_id, consultation_id, event_type, event_date, title, details, created_at |
| audit_logs | Security and traceability. | id, clinic_id, doctor_id, action, entity_type, entity_id, metadata, created_at |
| doctor_feedback | Pilot feedback and quality signals. | id, consultation_id, doctor_id, rating, issues_json, comments, created_at |

## Consultation status values

recording processing draft_ready edited approved rejected failed

## Timeline event types

chief_complaint diagnosis_documented_by_doctor medication_mentioned medication_change investigation_requested investigation_reviewed lifestyle_advice follow_up_plan procedure uncertain_item

# 9. AI Pipeline and Output Schema

The AI pipeline should be modular. Do not use one giant prompt for everything. Separate transcription, cleaning, extraction, validation, note rendering, and follow-up memory.

| Step | Input | Output | Safety rule |
| --- | --- | --- | --- |
| 1. Transcribe | Audio file | Transcript | Do not correct medical meaning. Keep uncertain words visible. |
| 2. Clean transcript | Raw transcript | Readable transcript | Preserve what was said; mark unclear sections. |
| 3. Extract structured JSON | Cleaned transcript | Clinical fields with source quotes | Only extract stated information. Do not infer. |
| 4. Validate | Transcript plus JSON | Issues and uncertainty flags | Flag hallucinations, missing evidence, low confidence items. |
| 5. Render draft note | Validated JSON | Doctor-facing note | Label as AI draft. Make editing easy. |
| 6. Doctor approval | Draft note | Approved note | Doctor must approve before storing as final. |
| 7. Update memory | Approved note | Timeline events and follow-up summary | Use approved content only. |

## Structured AI output

{ "chief_complaint": [], "history": [], "examination_findings": [], "diagnoses_documented_by_doctor": [], "medications_mentioned": [], "medication_changes": [], "investigations_requested": [], "investigations_reviewed": [], "lifestyle_advice": [], "follow_up_plan": [], "patient_instructions": [], "uncertain_items": [], "safety_flags": [] }

## Every extracted item should include evidence

{ "text": "Metformin continued twice daily", "source_quote": "doctor said: continue metformin morning and night", "confidence": "high" }

## System prompt rules

You are a clinical documentation assistant for Indian doctors. Your job is to convert a doctor-patient consultation transcript into a structured clinical documentation draft. Rules: 1. Do not diagnose. 2. Do not recommend treatment. 3. Do not add medical facts that were not stated. 4. Do not correct the doctor's plan. 5. Do not infer medication dosage unless clearly stated. 6. If something is unclear, add it to uncertain_items. 7. Preserve Indian drug names as spoken. 8. Handle Hinglish and mixed-language text. 9. Output only structured JSON. 10. Every important extracted item must be grounded in the transcript.

# 10. Safety, Privacy, and Compliance Guardrails

This product handles sensitive health information. Build privacy and safety into the MVP rather than treating them as later legal work.

| Area | MVP guardrail | Why |
| --- | --- | --- |
| Consent | Add a clear patient consent step before recording. Record consent status with consultation metadata. | Recording medical consultations requires explicit comfort and clarity. |
| Data minimization | Collect only what is needed for documentation and follow-up memory. | Reduces privacy risk and compliance burden. |
| Private storage | Store audio in private buckets with signed URLs. Never make audio public. | Raw audio is high-risk sensitive data. |
| Clinic isolation | Every row must be scoped to clinic_id and protected by row-level security. | Prevents cross-clinic data leaks. |
| Audit logs | Log create, view, edit, approve, delete, and export actions. | Creates traceability and trust. |
| Doctor approval | Never finalize AI notes automatically. | Doctor remains in control of clinical documentation. |
| AI disclaimers | Show AI draft label on every generated note. | Prevents the product from being mistaken for autonomous medical decision-making. |
| Deletion/export | Add admin process for deletion and export, even if manual at first. | Supports patient and clinic data rights. |
| No consumer PHI uploads | Do not put real identifiable patient data into consumer chat tools during testing. | Use de-identified or synthetic data until production controls are ready. |

## Required AI label

AI-generated draft note. Reviewed and approved by doctor before use. The AI does not diagnose, prescribe, or replace clinical judgment.

## MVP consent text for clinic testing

With your permission, this consultation may be recorded to help the doctor prepare accurate notes and remember your care history for future follow-ups. The recording is used only for documentation support. The doctor will review and approve any final note. You may ask not to be recorded.

## Safety red lines

The product must never diagnose independently.

The product must never recommend treatment independently.

The product must never change prescriptions without doctor approval.

The product must never hide uncertainty.

The product must never auto-share notes with patients without doctor approval.

The product must never train on clinic data without explicit contractual permission.

# 11. Pilot Plan

Run a controlled 30-day pilot with 2 to 3 friendly clinics after the core workflow works with synthetic data and safety guardrails are in place.

## Pilot goals

Measure whether doctors use the tool repeatedly, not just once.

Measure documentation time saved per consultation.

Measure doctor trust in generated notes.

Measure editing burden and common correction patterns.

Measure patient objections to recording.

Measure follow-up memory usefulness.

## Pilot metrics

| Metric | Target | How to measure |
| --- | --- | --- |
| Consultations recorded | At least 50 across pilot clinics | Count completed consultation records. |
| Draft generation time | 1 to 3 minutes after consultation | Log processing start and draft_ready times. |
| Doctor edit burden | Less than 30 percent of note changed | Compare AI draft to approved note. |
| Time saved | 2 to 5 minutes per consultation | Doctor self-report and observation. |
| Hallucination rate | Near zero high-severity hallucinations | Transcript-to-note QA plus doctor feedback. |
| Follow-up memory usage | Doctor opens memory before most follow-up visits | Track view events. |
| Willingness to pay | At least one paid commitment | Pilot close conversation. |

## Pilot feedback form

Was the note clinically useful? Rate 1 to 5.

What did the AI miss?

What did the AI get wrong?

Was any part unsafe or misleading?

How much editing did you do?

Did this save time?

Would you use this tomorrow?

Would you pay for this? If yes, how much per month?

What would stop you from using it daily?

## Pilot pricing experiments

Do not finalize pricing before pilot feedback. Start with simple ranges and test willingness to pay.

| Segment | Starting range | Notes |
| --- | --- | --- |
| Solo specialist | INR 2,999 to INR 7,999 per month | Depends on volume and perceived time saved. |
| Small clinic | INR 9,999 to INR 24,999 per month | Can price by doctor seat or consultation volume. |
| Premium specialty clinic | Higher custom pricing | Only after clear workflow ROI and support expectations are understood. |

# 12. Risk Register

| Risk | Why it matters | Mitigation |
| --- | --- | --- |
| Bad transcription | Indian clinics can be noisy; doctors may switch languages; drug names are hard. | Start with one specialty, collect corrections, mark uncertainty, allow fast editing, avoid promising perfection. |
| Hallucinated clinical note | A wrong note can damage trust and may be unsafe. | Ground every important item in source quotes, validate draft against transcript, add uncertain_items, require doctor approval. |
| Doctor feels extra work | If review takes too long, adoption fails. | One-click recording, fast drafts, templates, keyboard shortcuts, doctor-specific note style. |
| Patient recording discomfort | Patients may object or clinics may avoid recording. | Clear consent, visible notice, ability to skip recording, explain that doctor reviews all output. |
| Privacy/data leak | Health data is sensitive and reputationally risky. | Private storage, access controls, audit logs, least-privilege access, deletion/export process, legal review. |
| Scope creep | Solo founder time gets consumed by non-core features. | One specialty, one workflow, one killer feature: follow-up memory. |
| Too much competition in transcription | Generic scribes can look similar. | Position around clinical memory, timeline, follow-up context, and specialty workflows. |

# 13. Immediate Next Actions

This is the practical checklist to start building now.

Create a GitHub repository.

Create a ChatGPT Project for the startup.

Create README.md, PRODUCT.md, ROADMAP.md, and AGENTS.md.

Choose diabetes/endocrinology as the first specialty unless doctor discovery shows a stronger wedge.

Create 10 synthetic consultation transcripts covering common follow-up patterns.

Use ChatGPT to design the clinical note JSON schema.

Ask Codex to build the first Next.js app shell.

Build patient profile plus consultation timeline first.

Add audio recording and upload second.

Add transcription third.

Add structured AI note generation fourth.

Add doctor edit and approval workflow fifth.

Add patient timeline event generation sixth.

Add follow-up memory summary seventh.

Test only on fake or synthetic data first.

Recruit 5 doctors for prototype feedback.

Start live pilot only after consent, privacy, and approval workflow are in place.

FINAL FILTER: Every feature should answer: Will this help the doctor make a better-informed clinical decision while saving time? If not, do not build it now.

# 14. Appendix A - Synthetic Consultation Scenarios

Create synthetic transcripts before using real patient data. Use these scenarios to test transcription, extraction, uncertainty handling, and note rendering.

| Scenario | What to test |
| --- | --- |
| Diabetes follow-up with HbA1c improvement | Medication continuation, lifestyle advice, next lab date. |
| Diabetes follow-up with poor control | Medication change, diet explanation, unclear adherence. |
| Hinglish consultation | Mixed-language extraction and patient instruction summary. |
| Noisy consultation | Unclear dosage, uncertain_items behavior. |
| Patient mentions side effects | Capture complaint, medication relationship only if stated. |
| Doctor reviews lab report | Investigation reviewed, values, plan stated by doctor. |
| Missed follow-up | Timeline continuity and previous plan recall. |
| Multiple medications | Medication list and changes without hallucinating dose. |
| Lifestyle-heavy consultation | Diet, exercise, sleep, and follow-up advice. |
| Short repeat visit | Fast note generation and previous memory usage. |

# 15. Appendix B - Sample GitHub Issues for Codex

| Issue | Acceptance criteria |
| --- | --- |
| Set up Next.js app shell | Login route, dashboard route, patient route, shared layout, lint/build passing. |
| Create Supabase schema | All MVP tables created with clinic_id and timestamps; RLS placeholder policies added. |
| Build patient profile page | Shows demographics, consultation timeline, start new consultation button, loading/error states. |
| Build browser audio recorder | Start/stop recording, timer, permission handling, upload to private storage. |
| Create consultation processing route | Accepts audio file reference, creates processing status, returns draft_ready or failed. |
| Implement AI note editor | Displays structured draft, supports edit, approve, reject, and saves audit log. |
| Generate timeline events | Approved notes create timeline events for complaints, meds, tests, advice, and follow-up. |
| Create follow-up memory view | Shows previous visit summary, pending tests, medication changes, previous advice, and questions to clarify. |

# 16. Appendix C - Reference Notes

Use these sources for implementation details and policy checks. Always re-check current documentation before production launch.

| Topic | Source | Why it matters |
| --- | --- | --- |
| ChatGPT Projects | OpenAI Help Center: Projects in ChatGPT - https://help.openai.com/en/articles/10169521-using-projects-in-chatgpt | Projects keep chats, files, and custom instructions together for long-running work. |
| Codex | OpenAI Developers: Codex - https://developers.openai.com/codex/cloud | Codex can read, edit, run, and review code, and connect to GitHub workflows. |
| OpenAI API data controls | OpenAI Developers: Data controls - https://developers.openai.com/api/docs/guides/your-data | Production health workflows should use appropriate API/business data controls, not ad-hoc consumer chat uploads. |
| GPTs | OpenAI Help Center: GPTs in ChatGPT - https://help.openai.com/en/articles/8554407-gpts-faq | Custom GPTs are useful for internal assistants, but your product should use API workflows. |
| DPDP | MeitY: Digital Personal Data Protection Rules, 2025 - https://www.meity.gov.in/documents/act-and-policies/digital-personal-data-protection-rules-2025-gDOxUjMtQWa | India privacy compliance should be designed into consent, retention, security, and user rights flows. |
| ABDM | Ayushman Bharat Digital Mission - https://abdm.gov.in/ | Future interoperability should be considered, but MVP should be ABDM-ready rather than ABDM-dependent. |